## Start here
DataLund suite sample
Seven columns. Replace the rows with your projects and tasks.
Quick start
1. Import the three .pbiviz files from datalund.no
2. Load Projects and Tasks — relate Tasks[Project] → Projects[Project]
3. Bind matching column names (see below)
What to maintain
Projects → DataLund Task List: Project, RAG, Group, Project lead, Progress, Start Date, End Date
Tasks → Gantt + Resource Load: Task, Start Date, End Date, Progress, Group, Resource, Project
Progress is 0–100. RAG is Red / Amber / Green (or Rød / Gul / Grønn).
Same start and end date = milestone. Duration and Tooltips are optional later — not in this starter.
Put Task List on the page, click a project — Gantt and Resource Load follow.
https://datalund.no
Free Power BI visuals · support@datalund.no

## Projects
Project | RAG | Group | Project lead | Progress | Start Date | End Date
North Sea Hub | Green | Delivery | Ada Ng | 72 | 2026-06-11 | 2026-09-19
Arctic Link | Amber | Delivery | Bo Berg | 45 | 2026-05-12 | 2026-08-30
Yard Retrofit | Red | Initiation | Cara Diaz | 18 | 2026-07-11 | 2026-08-20
Digital Twin v2 | Green | Build | Dan Okonkwo | 88 | 2026-04-12 | 2026-08-25
Port Expansion | Amber | Plan | Finn Olsen | 12 | 2026-08-15 | 2027-02-06

## Tasks
Task | Start Date | End Date | Progress | Group | Resource | Project
Requirements | 2026-06-11 | 2026-06-25 | 100 | Delivery | Ada Ng | North Sea Hub
API design | 2026-07-01 | 2026-07-20 | 75 | Delivery | Sam Ortiz | North Sea Hub
FAT prep | 2026-08-20 | 2026-09-05 | 20 | Delivery | Ada Ng | North Sea Hub
Cable pull | 2026-07-01 | 2026-08-20 | 40 | Delivery | Bo Berg | Arctic Link
Weather hold | 2026-08-10 | 2026-08-18 | 0 | Delivery | Riley Chen | Arctic Link
On-call week | 2026-08-18 | 2026-08-24 | 0 | Delivery | Bo Berg | Arctic Link
Scope workshop | 2026-07-11 | 2026-07-25 | 50 | Initiation | Cara Diaz | Yard Retrofit
Scope freeze | 2026-08-12 | 2026-08-12 | 0 | Initiation | Cara Diaz | Yard Retrofit
Integration | 2026-07-01 | 2026-08-10 | 85 | Build | Sam Ortiz | Digital Twin v2
UAT | 2026-08-11 | 2026-08-25 | 30 | Build | Ada Ng | Digital Twin v2
Permit draft | 2026-08-15 | 2026-10-01 | 10 | Plan | Finn Olsen | Port Expansion
Stakeholder map | 2026-08-20 | 2026-09-15 | 5 | Plan | Jordan Lee | Port Expansion